## Action Tracker
Action ID | Source | Reference | Related Risk | Action | Owner | Status (at 12-Jun-2026) | Due Date | Dependency | Closure Evidence
ACT-01 | Internal audit | ISO-001 | R-001 to R-012 | Record risk-owner approval of the treatment plans and the residual-risk decision for each of the 12 risks | Top Management (decisions recorded by each risk owner) | Completed 12-Jun-2026; verification pending | 2026-06-12 | None | Management-Review-Minutes.md, section 2 (Risk Owner column). Verification at follow-up audit.
ACT-02 | Internal audit | ISO-002 | None | Determine which interested party requirements the ISMS addresses and record the determination in the Interested Parties Register | IT Manager | Open | 2026-07-31 | None | Updated Interested Parties Register showing which requirements are addressed and the related scope item, risk or control
ACT-03 | Internal audit | ISO-003 | R-001 to R-012 | Add a confidentiality, integrity and availability field to the Risk Register | IT Manager | Open | 2026-07-31 | None | Updated Risk Register with the C/I/A field completed for all 12 risks
ACT-04 | Internal audit | ISO-004 | R-001 to R-012 | Define the risk assessment interval (annual) in the methodology and record the assessment date in the Risk Register | IT Manager | Open | 2026-07-31 | None | Updated Risk Assessment Methodology and Risk Register with assessment date
ACT-05 | Management review | Clause 5.3; prerequisite for ACT-06 | R-004 | Assign responsibility and authority for the Security/Compliance function | Top Management | Open | 2026-07-31 | None | Documented assignment of responsibility and authority
ACT-06 | Internal audit; Planned control | ISO-005; SoA 5.35 | R-004 | Introduce independent co-review of privileged access | Security/Compliance function (role to be assigned) | Open | 2026-09-30 | ACT-05 | First quarterly privileged access review co-reviewed by the Security/Compliance function; SoA 5.35 updated
ACT-07 | Management review | Planned control; SoA 8.9 | R-010 | Implement cloud configuration monitoring. R-010 residual risk is not accepted. | Infrastructure Operations | Open | 2026-08-31 | None | Evidence of configuration monitoring in operation; ITGC test of the control; SoA 8.9 updated
ACT-08 | Management review | Planned controls; SoA 8.25, 8.28 | R-011 | Define and implement secure SDLC and secure coding controls | Engineering Manager | Open | 2026-11-30 | None | Approved secure SDLC and secure coding standards; evidence of application; SoA 8.25 and 8.28 updated
ACT-09 | Management review | Clause 6.2 | ISMS-wide | Establish documented information security objectives, with owners, measures and targets | Top Management | Open | 2026-09-30 | None | Documented information security objectives with assigned owners, measures and targets
ACT-10 | Management review | R-001 condition | R-001 | Extend access review testing to Q2 to Q4 2026 | Application Owners | Open | 2026-12-31 | None | Q2 to Q4 access review evidence and updated UAM-01 workpaper
ACT-11 | Management review | R-006 condition | R-006 | Add periodic restore testing for backups | Infrastructure Operations | Open | 2026-09-30 | None | Restore test records and an updated OPS-01 workpaper
ACT-12 | Management review | R-009 condition | R-009 | Add MFA enforcement testing to the next audit cycle | IT Manager | Open | 2027-03-31 | None | MFA enforcement test workpaper and evidence
ACT-13 | Management review | R-012 condition | R-012 | Review the connected-application inventory annually | IAM Administrator | Open | 2026-12-31 | None | Connected-application inventory review record
ACT-14 | Management review | Clause 9.3.2(d)(4) | ISMS-wide | Review and report performance against information security objectives at the next management review | Top Management | Open | 2027-06-30 | ACT-09 | Performance results documented in the next Management Review Minutes